## Sheet1
Dissertation Timeline
Task No. | Description | Additional information/ Dates | Resources Needed | Progress | To be completed by/ Submission date? | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
[6 empty] | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28 | week 29 | week 30 | week 31 | week 32 | week 33 | week 34 | week 35 | week 36 | week 37 | week 38 | week 39 | week 40
1 | Topic finding
1.1 | Read through lecture notes and assignments for topic inspiration |  |  | In progress | bar: September week 1
1.2 | Create a mind map of possible topics and what interests me |  |  | In progress | bar: September week 1 to September week 2
1.3 | Select and start learning to use reference management software |  |  | In progress | bar: September week 2 to September week 4
1.4 | Preliminary research: is there enough sources data or literature available? |  |  | Not started | bar: September week 2 to September week 4
1.5 | Refine topic into research questions |  |  | Not started | bar: September week 3
1.6 | Write preliminary objectives for achieving my research question |  |  | Not started | bar: September week 3
1.7 | Meet with supervisor to discuss topic suitability, research question, and objectives |  |  | Not started | bar: September week 4 to October week 5
1.8 | Amend topic focus/ plan based on supervisor feedback |  |  | Not started | bar: September week 4 to October week 5
2 | Proposal
2.1 | Write up agreed research question and objectives |  |  | Not started | bar: October week 5
2.3 | Research methodologies |  |  | Not started | bar: October week 5 to October week 7
2.4 | Prepare ethical statement |  |  | Not started | bar: October week 7
2.5 | Detailed planning (what chapters/ sections?, what will they include?) |  |  | Not started | bar: October week 7 to October week 8
2.6 | Create bibliography and reference list |  |  | Not started | bar: October week 7 to October week 8
2.7 | Meet with supervisor to review proposal before submission |  |  | Not started | bar: October week 8 to November week 9
2.8 | Submit proposal |  |  | Not started |  | November week 9: Submit!
3 | Literature review
3.1 | Refresh searching skills (attend workshop or complete online tutorial) |  |  | Not started | bar: September week 1 to September week 3
3.2 | Carry out searches |  |  | Not started
3.3 | Read through materials gathered picking out common themes and debates |  |  | Not started
3.4 | Start writing |  |  | Not started
3.5 | Speak to supervisor have I missed any of the major sources/ papers? |  |  | Not started
3.6 | Proof reading |  |  | Not started
3.7 | Check in with Supervisor | bar: November week 11 to November week 12
3.8 | Finalise and submit literature review |  |  | Not started |  | December week 13: Submit!
4 | Methodology
4.1 | Select and prepapre methods |  |  | Not started
4.2 | Critique methodology |  |  | Not started
4.3 | Create ethical statement |  |  | Not started
4.4 | Meet supervisor for approval of ethics |  |  | Not started
4.5 | Plan dates for gathering data |  |  | Not started
4.5 | Update bibliograph and write up methodologies section |  |  | Not started
5 | Data collection and analysis
5.1 | Test selected methods |  |  | Not started
5.2 | Review results and methodology |  |  | Not started
5.3 | Carry out data collection |  |  | Not started
5.4 | Record results |  |  | Not started
5.5 | Read and complete tutorials on analysing and presenting data |  |  | Not started
5.6 | Validate data |  |  | Not started
5.7 | Carry out initial anaylisis of the results |  |  | Not started
5.8 | Write up 'stories' what does the data say? |  |  | Not started
5.9 | Check 'data stories' against the data |  |  | Not started
5.10. | Write up data analysis section |  |  | Not started
6 | Writing
6.1 | Write up remaining sections |  |  | Not started
6.2 | Review and imporve writing |  |  | Not started
6.3 | Proofread |  |  | Not started
6.4 | Add charts, displays to data anaysis sections. |  |  | Not started
6.5 | Finish reference list and bibliogrpahy |  |  | Not started
6.6 | Add in front page, contents, abstract, appendices etc. |  |  | Not started
7 | Gathering together/ finishing off
7.1 | Final proof read and re-writing |  |  | Not started
7.2 | Arrange printing and binding |  |  | Not started
7.3 | Submit and celebrate! |  |  | Not started